## 18012023
ESG and Green Team meeting
In Attendance: | Ivan, Francesco, Filippo, Maryanne, Ramesh, Freya, Jade, Alex, Saakshee, Douglas, Michele
Absent: | Amanda, Terry, Brad, Taffryn |  |  | Last updated 18/01
TOPIC | PLAN OF ACTION/ COMMENTS | UPDATES | ADDITIONAL INFO | STATUS
SINGLE USE OF PLASTICS
Bath amenities | Floris products offered in large format (300ml) in all of our suites & LS guest rooms & the rest of the rollout will be completed by year end 2022 | 95 Rooms to be turned around / KILKER to assign with project led by ENG (Shelving /bathroom) - 2months lead. Kilker working in the price with 3rd part vendor for the stone. | Ivan will update in the next meeting after checking with Vaida. Suggestions made on new shelf to have a hole on the side to avoid mould. Awaiting delivery of cermaic bottles - shelves ot to be installed this year | HSKP
Water bottles | • No bottling plant in place as was put on hold before due to cost. • Employees will get aluminium bottles with FS logo. Looked at Chilly bottles brand for now and aim to order 500 bottles • Sporty bottles at coffee/ water station: tried different options but they still have plastic parts and are £1 more expensive per bottle | 4 X Boxes delivered at FSPL - awaiting for rollout (IM) | Care with employees using the bottles for personal use. MR to send communication - is still an issue? (MR) Bottles are set up for the running station and by the coffee station in the lobby. New starter welcome bottle IM requesting samples. IM - still waiting for final samples as previous ones had a very poor quality | PR/P&C
Recycling | • Suggestions of including recycling bins in guest rooms may be pointless as there is no segregation and they may go to the same place • HSKP Pantries segregation bins to be removed. | HSK req for redesign Pantry for 3 BINS - Bins are to be emptied more frequently but posses a challenge ( IM to review current provision/ order / ENG to support with shelving) |  | HSKP
SUSTAINABLE F&B
Food waste training | • For all F&B employees – 30 minutes video with quiz at the end. MR to check with Cristina if we can send to all F&B employees to complete and look into embedding into EMBARK in the future. Deadline was end of Q2/2022 | CH (P&C) - agreed to put in training in Work Day and commencing 1st SEP 2022 / Two types of training ( F&B - EMABARK & 2. 30 Min Work Day training) | F&B Division is 100%, remainde rof the hotel still at 45% as per last report from Cristina | P&C
Food waste diversion | • Issues with local legislation, so park for now ( Park for now due to local laws restrictions) | By law FSPL can donate - FOOD to charity - awaiting nominated Partnership list from Corporate . | Saakshee will send out an email to Caitrin VP ESG. Email sent - | ON HOLD - will be asked during Corp ESG Call on 1st Feb
Food donation programs | To explore - staff dropping off initiative TO/FROM to work for homeless (awaiting more info on Product waste / quantity/packing provisions) | Logistic might be a problem for consistency on PICK up /DROP off on food donation | 1 off donation initiatives welcomed, similar to the Ukraine relief previously | ON HOLD - will be asked during Corp ESG Call on 1st Feb
Food Waste | Michele to update stats and tracker to control plate waste |  |  | Michele
Mini Bar- BLACK label / Bacardi are Plastic miniature bottles | Are we exploring to Glass/ alternative solution | Beverages 80% - Black label - Doug checking with TRI /HAM. What kind of plastic? Recycle plastic. Pending. | Working on it- to check globally for non plastic use for mini bar items F&B | F&B - Doug to get info from HAM/TRI
EXTERNAL COMMUNICATIONS
EMPLOYEE ENGAGEMENT
ESG HUB / WASTE MANAGEMENT CHECKLIST
Waste Audit and Data Collection
Has your property conducted a self organized waste audit within the last 2 years? |  | Not completed | No submission on Water MGT Checklist required to Corporate , internal process to be provisioned - Currently ENG have in place - Jonathan has access to pull reports on ESG HUB - key control and measures. Need template and Saakshee will reach out to Caitrine. Share in meetings, record keeping. Create a tab which vendors have, add additional field in Birchstreet. Saakshee will reach out.
Has your property conducted a waste audit in the last 4 years? |  | Not completed
Have you reached out to all of your waste vendors to request monthly reports with actual volume or weight data instead of estimates? |  | Completed
Is waste being reported in HEP, covering every month since January 2022? |  | Not completed
Have you reported historical waste data going back to your baseline year (2018 or year of opening)? |  | Not completed
Waste Reduction Activities
Have you developed goals to increase your recycling rates and reduce the amount of waste sent to landfill from your property? |  | Not completed | ACM to provide Automated report of Waste / PDM to provide OIL & FOOD report via their portals
Has your watse hauler isnatlled compactor monitors or offered opportunities for on demand pick up instead of scheduled waste hauling? |  | Completed
Have you inquired about opportunities for waste training or signage (Often provided by local haulers free of charge)? |  | Completed
If your current waste vendor isnt able to divert a waste category from landfill, have you explored other solutions locally? |  | N/A - Ian showed dashboard of ACM waste tracker/ building data
If your property currently recycles, do you offer recycling containers in all guest rooms, common spaces or heart of house areas? |  | N/A - Ian showed dashboard of ACM waste tracker/ building data
Any Other Business
Touch Point of Hotel / What have we achieved ? | Filippo and Freya to also complete an internal audit on plastic use in our rooms audit ( non -ops to support) | Departments to check what kind of plastic is used, how many reports, how much paper is used, etc. Flilippo will audit. | Next week Filippo is gathering some information and Engineeering to explore different door knobs. • | See below - Plastic Police - Spa updates from Taffryn
Engineering calling cards | to replace plastic with non plastic calling cards | JT to reach out to his contact and provide feedback
PLASTIC POLICE
Evian found in mybars | Mybar stock remaining, Baptiste to get a count so we can create plan to utalize remining stock |  | Dr Burgener mini bar offer is in investigation. Email sent 8/2 | Spa
Spa products | Many spa products with excessive wrapping, especially candles and nail files. |  | Lower Lodge candles project under way for packaging and Charline is looking at alternate nail file options with Ian | Spa
Spa lockers | Plastic mouthwash cups |  |  | Spa
Rooms - LWC kits | Plastic packaging |  | LWC kits will no longer be used in 2023 | Only avlb on request not as standard set up
IRD - Mybar package | Popcorn is not sustainable |  | Baptiste to look at options | Doug reviewing
NEW IDEAS
Zest ESG Quiz |  |  | Creating more awareness within teams & colleagues | Maryanne / Jade to review for Dec.
Possible inclusion of Kcal on Zest menu for key/consistent items like Fish & Chips/Burgers/Chicken etc |  |  |  | Alex to speak with Marcin - seek inputs/advise.
Creating a Green Team 'Org chat' to create more awareness |  |  |  | Jade to add Michele to Org chart
Creating an ESG suggestion stand/box |  |  | Terry to assist - made from sustainable material & a lot of creativity! | Terry - completed by last week of Jan 2023
Looking at 'green' incentives for best idea on a quarterly basis |  |  | P&C to assist | Maryanne to explore & start INH with Spa/HSKP for ideas.
Plant a tree in Royal Parks with FSPL Plaque |  |  |  | Ramesh to review & advise

## 05012023
ESG and Green Team meeting
In Attendance: | Ramesh, Amanda, Brad, Maryanne
Absent: | Francesco, Saakshee, Agnieszka, Jonathan, Derek, Matthias, Jade, Freya, Ian, Alex, |  |  | Last updated 06/01
TOPIC | PLAN OF ACTION/ COMMENTS | UPDATES | ADDITIONAL INFO | STATUS
SINGLE USE OF PLASTICS
Bath amenities | Floris products offered in large format (300ml) in all of our suites & LS guest rooms & the rest of the rollout will be completed by year end 2022 | 95 Rooms to be turned around / KILKER to assign with project led by ENG (Shelving /bathroom) - 2months lead. Kilker working in the price with 3rd part vendor for the stone. | Ivan will update in the next meeting after checking with Vaida. Suggestions made on new shelf to have a hole on the side to avoid mould. Dec 31st deadline for completion of shelves
Dry amenities | They have been ordered and waiting for delivery |  | Only combs and shower caps left to use up
Water bottles | • No bottling plant in place as was put on hold before due to cost. • Employees will get aluminium bottles with FS logo. Looked at Chilly bottles brand for now and aim to order 500 bottles • Sporty bottles at coffee/ water station: tried different options but they still have plastic parts and are £1 more expensive per bottle | 4 X Boxes delivered at FSPL - awaiting for rollout (IM) | Care with employees using the bottles for personal use. MR to send communication. Bottles are set up for the running station and by the coffee station in the lobby. New starter welcome bottle IM requesting samples. IM | Samples of welcome kit ready next meeting
Recycling | • Suggestions of including recycling bins in guest rooms may be pointless as there is no segregation and they may go to the same place • HSKP Pantries segregation bins to be removed. | HSK req for redesign Pantry for 3 BINS - Bins are to be emptied more frequently but posses a challenge ( IM to review current provision/ order / ENG to support with shelving)
SUSTAINABLE F&B
Food waste training | • For all F&B employees – 30 minutes video with quiz at the end. MR to check with Cristina if we can send to all F&B employees to complete and look into embedding into EMBARK in the future. Deadline was end of Q2/2022 | CH (P&C) - agreed to put in training in Work Day and commencing 1st SEP 2022 / Two types of training ( F&B - EMABARK & 2. 30 Min Work Day training) | F&B Division is 100%, remainde rof the hotel is at 45%
Food waste diversion | • Issues with local legislation, so park for now ( Park for now due to local laws restrictions) | By law FSPL can donate - FOOD to charity - awaiting nominated Partnership list from Corporate . | Saakshee will send out an email to Caitrin VP ESG. Email sent - | ON HOLD
Food donation programs | To explore - staff dropping off initiative TO/FROM to work for homeless (awaiting more info on Product waste / quantity/packing provisions) | Logistic might be a problem for consistency on PICK up /DROP off on food donation | 1 off donation initiatives welcomed, similar to the Ukraine relief previously | ON HOLD
Food Waste | • Nothing in place here • There was a pilot programme happening at FS New Orleans and Dubai but no news yet on how has developed, successes and ROI examples to check with Corporate office if there have been some results from that pilot as yet | Waiting for Gianluca for the results/ we have budget alocated for Q3 | Winnow - Francesco to follow up with corporate for further details, all hotels to start with Winnow. F&B to follow up.
Mini Bar- BLACK label / Bacardi are Plastic miniature bottles | Are we exploring to Glass/ alternative solution | Beverages 80% - Black label - Doug checking with TRI /HAM. What kind of plastic? Recycle plastic. Pending. | Working on it- to check globally for non plastic use for mini bar items F&B | Doug has found alternative samples for next meeting
EXTERNAL COMMUNICATIONS
EMPLOYEE ENGAGEMENT
ESG HUB / WASTE MANAGEMENT CHECKLIST
Waste Audit and Data Collection
Has your property conducted a self organized waste audit within the last 2 years? |  | Not completed | No submission on Water MGT Checklist required to Corporate , internal process to be provisioned - Currently ENG have in place - Jonathan has access to pull reports on ESG HUB - key control and measures. Need template and Saakshee will reach out to Caitrine. Share in meetings, record keeping. Create a tab which vendors have, add additional field in Birchstreet. Saakshee will reach out.
Has your property conducted a waste audit in the last 4 years? |  | Not completed
Have you reached out to all of your waste vendors to request monthly reports with actual volume or weight data instead of estimates? |  | Completed
Is waste being reported in HEP, covering every month since January 2022? |  | Not completed
Have you reported historical waste data going back to your baseline year (2018 or year of opening)? |  | Not completed
Waste Reduction Activities
Have you developed goals to increase your recycling rates and reduce the amount of waste sent to landfill from your property? |  | Not completed | ACM to provide Automated report of Waste / PDM to provide OIL & FOOD report via their portals
Has your watse hauler isnatlled compactor monitors or offered opportunities for on demand pick up instead of scheduled waste hauling? |  | Completed
Have you inquired about opportunities for waste training or signage (Often provided by local haulers free of charge)? |  | Completed
If your current waste vendor isnt able to divert a waste category from landfill, have you explored other solutions locally? |  | N/A - Ian showed dashboard of ACM waste tracker/ building data
If your property currently recycles, do you offer recycling containers in all guest rooms, common spaces or heart of house areas? |  | N/A - Ian showed dashboard of ACM waste tracker/ building data
Any Other Business
Touch Point of Hotel / What have we achieved ? | Filippo and Freya to also complete an internal audit on plastic use in our rooms audit ( non -ops to support) | Departments to check what kind of plastic is used, how many reports, how much paper is used, etc. Flilippo will audit. | Next week Filippo is gathering some information and Engineeering to explore different door knobs. • | See below - Plastic Police
Engineering calling cards | to replace plastic with non plastic calling cards | JT to reach out to his contact and provide feedback
PLASTIC POLICE
Evian found in mybars | Mybar stock remaining, Baptiste to get a count so we can create plan to utalize remining stock |  | Black Pearl, Linda Meredith, Cochine, Holistic Silk
Spa products | Many spa products with excessive wrapping, especially candles and nail files.
Spa amenities | cotton tips and pads in plastic |  | HSK to assist in utalizing remaining stock ready for dry amenity launch in NOV
Spa lockers | Plastic mouthwash cups
Rooms - LWC kits | Plastic packaging |  | LWC kits will no longer be used in 2023
Rooms - newspaper bags | Plastic bags |  | This is a temporary solution, delivery is soon of cloth bags
IRD - Mybar package | Popcorn is not sustainable |  | Baptiste to look at options
NEW IDEAS
Zest ESG Quiz |  |  | Creating more awareness within teams & colleagues | Maryanne / Jade to review for Dec.
Possible inclusion of Kcal on Zest menu for key/consistent items like Fish & Chips/Burgers/Chicken etc |  |  |  | Alex to speak with Marcin - seek inputs/advise.
Creating a Green Team 'Org chat' to create more awareness |  |  | Saakshee to send G/Team names to Freya for creating a template per Brand DNA ' Maryanne to post in BOH areas. | Saakshee/Freya/Maryanne - completed by 1st week of Dec.
Creating an ESG suggestion stand/box |  |  | Terry to assist - made from sustainable material & a lot of creativity! | Terry - completed by 1st week of Dec
Looking at 'green' incentives for best idea on a quarterly basis |  |  | P&C to assist | Maryanne to explore & start INH with Spa/HSKP for ideas.
Plant a tree in Royal Parks with FSPL Plaque |  |  |  | Ramesh to review & advise

## 12102022
ESG and Green Team meeting
In Attendance: | Ian, Alex, Filippo, Brad, Ivan, Terry, Ramesh, Freya, Baptiste
Absent: | Francesco, Saakshee, Agnieszka, Jonathan, Derek, Matthias,Amanda |  |  | Last updated 12/10
TOPIC | PLAN OF ACTION/ COMMENTS | UPDATES | ADDITIONAL INFO | STATUS
SINGLE USE OF PLASTICS
Bath amenities | Floris products offered in large format (300ml) in all of our suites & LS guest rooms & the rest of the rollout will be completed by year end 2022 | 95 Rooms to be turned around / KILKER to assign with project led by ENG (Shelving /bathroom) - 2months lead. Kilker working in the price with 3rd part vendor for the stone. | Ivan will update in the next meeting after checking with Vaida. Suggestions made on new shelf to have a hole on the side to avoid mould. Dec 31st deadline for completion of shelves
Dry amenities | They have been ordered and waiting for delivery |  | Only combs and shower caps left to use up
Water bottles | • No bottling plant in place as was put on hold before due to cost. • Employees will get aluminium bottles with FS logo. Looked at Chilly bottles brand for now and aim to order 500 bottles • Sporty bottles at coffee/ water station: tried different options but they still have plastic parts and are £1 more expensive per bottle | 4 X Boxes delivered at FSPL - awaiting for rollout (IM) | Care with employees using the bottles for personal use. MR to send communication. Bottles are set up for the running station and by the coffee station in the lobby. New starter welcome bottle IM requesting samples. IM | Samples of welcome kit ready next meeting
Laundry presentation | • Fabric cover presented at the moment for guests. Basket with paper cover and hanger has no cover • For employees – when done in-house there is no cover but when done outside the company send with a plastic cover • Plastic roll in HSKP to be replaced with more eco friendly option. IC to liaise with Silvia Grey to check if they have other non-plastic options. IM to confirm completion date | Sylvia Grey Agreed with Plastic free and Valet using recyclable plastic | Scott Taber - 19/09/22- PLASTIC FREE FSPL already switched internally, pending SG, change to biodegradable Scott Taber back in FSPL on the 10th and 11th of October | Silvia Grey has been issued stock to utalize to comply. RESOLVED
Recycling | • Suggestions of including recycling bins in guest rooms may be pointless as there is no segregation and they may go to the same place • HSKP Pantries segregation bins to be removed. | HSK req for redesign Pantry for 3 BINS - Bins are to be emptied more frequently but posses a challenge ( IM to review current provision/ order / ENG to support with shelving)
SUSTAINABLE F&B
Food waste training | • For all F&B employees – 30 minutes video with quiz at the end. MR to check with Cristina if we can send to all F&B employees to complete and look into embedding into EMBARK in the future. Deadline was end of Q2/2022 | CH (P&C) - agreed to put in training in Work Day and commencing 1st SEP 2022 / Two types of training ( F&B - EMABARK & 2. 30 Min Work Day training) | Cristina will send out a list on 1st of Sep. Email sent- training ongoing but needs more momentum, all dpts are to assist in this.
Food waste diversion | • Issues with local legislation, so park for now ( Park for now due to local laws restrictions) | By law FSPL can donate - FOOD to charity - awaiting nominated Partnership list from Corporate . | Saakshee will send out an email to Caitrin VP ESG. Email sent -
Food donation programs | To explore - staff dropping off initiative TO/FROM to work for homeless (awaiting more info on Product waste / quantity/packing provisions) | Logistic might be a problem for consistency on PICK up /DROP off on food donation | 1 off donation initiatives welcomed, similar to the Ukraine relief previously | ON HOLD
Food waste AI solutions | • Nothing in place here • There was a pilot programme happening at FS New Orleans and Dubai but no news yet on how has developed, successes and ROI examples to check with Corporate office if there have been some results from that pilot as yet | Waiting for Gianluca for the results/ we have budget alocated for Q3 | Winnow - Francesco to follow up with corporate for further details, all hotels to start with Winnow. F&B to follow up.
controlling food quantity in ZEST | reduce food waste | Mary-anne to try to find figures on head counts for staff canteen | Poster campaign to be created and Alex to have waste amounts for next newsletter to improve awareness
Mini Bar- BLACK label / Bacardi are Plastic miniature bottles | Are we exploring to Glass/ alternative solution | Beverages 80% - Black label - Doug checking with TRI /HAM. What kind of plastic? Recycle plastic. Pending. | Working on it- to check globally for non plastic use for mini bar items F&B | Doug has found alternative samples for next meeting
EXTERNAL COMMUNICATIONS
Freya is working with FS Corporate on creating a ESG landing page on the FS.com
EMPLOYEE ENGAGEMENT
All ESG team members to ensure Newsletter is circulated in their respective areas
Cafeteria food waste | Alex to gather data on wastage, OCT newsletter to focus on this to increase employee education and awareness |  | Posters to also be created / circulated
ESG HUB / WASTE MANAGEMENT CHECKLIST
|  | • First two questions: NOT COMPLETED// • Question 3: COMPLETED Questions 4 & 5: NOT COMPLETEDIM to check with Corporate in regards to resources for a self-organised auditTerry to do a small presentation how to read/use data from HEP | No submission on Water MGT Checklist required to Corporate , internal process to be provisioned - Currently ENG have in place - Jonathan has access to pull reports on ESG HUB - key control and measures. Need template and Saakshee will reach out to Caitrine. Share in meetings, record keeping. Create a tab which vendors have, add additional field in Birchstreet. Saakshee will reach out.
|  | • Q1 – NOT COMPLETED • Q2 & 3 – COMPLETED • Q4 & 5 – N/A Ian showed dashboard of ACM waste tracker/ building data | ACM to provide Automated report of Waste / PDM to provide OIL & FOOD report via their portals
Any Other Business
How conscious are we with reducing/ recycling / ESG programme ? |  | Data showed via ACM | Ian to have report for OCT newsletter
Touch Point of Hotel / What have we achieved ? | Filippo and Freya to also complete an internal audit on plastic use in our rooms audit ( non -ops to support) | Departments to check what kind of plastic is used, how many reports, how much paper is used, etc. Flilippo will audit. | Next week Filippo is gathering some information and Engineeering to explore different door knobs. • | See below - Plastic Police
Water bottles for new starters | A welcome box for new starters including a FS metal bottle and notepad | Christian is working on this. Pending. | P&C will focus on this now. IM waiting for samples | Welcome kit sample ready next meeting
Entegra presentation/ discussion | 3 projects to work on: Bees project/ Spout pencil and Hydroponcisis |  | Ian will get some more information - Project bees too expensive. IM in direct talks to sprout pencil
Community out reach: Maryanne to share with the hotel the Felix project /voluntering project to help others
Engineering calling cards | to replace plastic with non plastic calling cards | JT to reach out to his contact and provide feedback
PLASTIC POLICE
Evian found in mybars | Mybar stock remaining, Baptiste to get a count so we can create plan to utalize remining stock |  | Black Pearl, Linda Meredith, Cochine, Holistic Silk
Spa products | Many spa products with excessive wrapping, especially candles and nail files.
Spa amenities | cotton tips and pads in plastic |  | HSK to assist in utalizing remaining stock ready for dry amenity launch in NOV
Spa lockers | Plastic mouthwash cups
Rooms - LWC kits | Plastic packaging |  | LWC kits will no longer be used in 2023
Rooms - newspaper bags | Plastic bags |  | This is a temporary solution, delivery is soon of cloth bags
IRD - Mybar package | Popcorn is not sustainable |  | Baptiste to look at options

## 29092022
ESG and Green Team meeting
In Attendance: | Sebastian, Ian, Alex, Filippo, Saakshee, Brad, Ivan, Terry, Maryanne and Fransesco
Absent: | Freya, Baptiste, Agnieszka, Jonathan, Derek, Matthias. |  |  | Last updated 29/09
TOPIC | PLAN OF ACTION/ COMMENTS | UPDATES | ADDITIONAL INFO | STATUS
SINGLE USE OF PLASTICS
Bath amenities | Floris products offered in large format (300ml) in all of our suites & LS guest rooms & the rest of the rollout will be completed by year end 2022 | 95 Rooms to be turned around / KILKER to assign with project led by ENG (Shelving /bathroom) - 2months lead. Kilker working in the price with 3rd part vendor for the stone. | Ivan will update in the next meeting after checking with Vaida. Suggestions made on new shelf to have a hole on the side to avoid mould. Dec 31st deadline for completion of shelves
Dry amenities | They have been ordered and waiting for delivery |  | Only combs and shower caps left to use up
Water bottles | • No bottling plant in place as was put on hold before due to cost. • Employees will get aluminium bottles with FS logo. Looked at Chilly bottles brand for now and aim to order 500 bottles • Sporty bottles at coffee/ water station: tried different options but they still have plastic parts and are £1 more expensive per bottle | 4 X Boxes delivered at FSPL - awaiting for rollout (IM) | Care with employees using the bottles for personal use. MR to send communication. Bottles are set up for the running station and by the coffee station in the lobby. New starter welcome bottle IM requesting samples. IM
My Bar | • Currently offering Evian plastic bottle / Search different options Look at Acqua Panna product as an option – IM/ FG | A/Panna to stay in minibar /comp offering as part of switch over | DONE, price change pending with FDS / Opera | COMPLETED
Laundry presentation | • Fabric cover presented at the moment for guests. Basket with paper cover and hanger has no cover • For employees – when done in-house there is no cover but when done outside the company send with a plastic cover • Plastic roll in HSKP to be replaced with more eco friendly option. IC to liaise with Silvia Grey to check if they have other non-plastic options. IM to confirm completion date | Sylvia Grey Agreed with Plastic free and Valet using recyclable plastic | Scott Taber - 19/09/22- PLASTIC FREE FSPL already switched internally, pending SG, change to biodegradable Scott Taber back in FSPL on the 10th and 11th of October
F&B disposables | • All plastic free already, however FG to check if take away lids are biodegradable and PLA free too | Few PLA Lids remains that is non recyclable (stock to be finished in few weeks) / New order are Recyclable Lids at FSPL 17/08/2022 | Ian placed order - TBC Bins: Leave glass bins, cannot buy bins with lid due to hygiene reasons. - Plastic bag in the pantries (training required for staff) | complete
Straws | • All plastic free already |  |  | COMPLETE
Recycling | • Suggestions of including recycling bins in guest rooms may be pointless as there is no segregation and they may go to the same place • HSKP Pantries segregation bins to be removed. | HSK req for redesign Pantry for 3 BINS - Bins are to be emptied more frequently but posses a challenge ( IM to review current provision/ order / ENG to support with shelving)
Soap recycling | • Working with La Bottega that can recycle | IC to start process with La Bottega. To use old soap from old recycling projects. | Start with one floor- ongoing IC
SUSTAINABLE F&B
Food waste training | • For all F&B employees – 30 minutes video with quiz at the end. MR to check with Cristina if we can send to all F&B employees to complete and look into embedding into EMBARK in the future. Deadline was end of Q2/2022 | CH (P&C) - agreed to put in training in Work Day and commencing 1st SEP 2022 / Two types of training ( F&B - EMABARK & 2. 30 Min Work Day training) | Cristina will send out a list on 1st of Sep. Email sent- training ongoing but needs more momentum, all dpts are to assist in this.
Food waste diversion | • Issues with local legislation, so park for now ( Park for now due to local laws restrictions) | By law FSPL can donate - FOOD to charity - awaiting nominated Partnership list from Corporate . | Saakshee will send out an email to Caitrin VP ESG. Email sent -
Food donation programs | To explore - staff dropping off initiative TO/FROM to work for homeless (awaiting more info on Product waste / quantity/packing provisions) | Logistic might be a problem for consistency on PICK up /DROP off on food donation | 1 off donation initiatives welcomed, similar to the Ukraine relief previously
Food waste AI solutions | • Nothing in place here • There was a pilot programme happening at FS New Orleans and Dubai but no news yet on how has developed, successes and ROI examples to check with Corporate office if there have been some results from that pilot as yet | Waiting for Gianluca for the results/ we have budget alocated for Q3 | Winnow - Francesco to follow up with corporate for further details, all hotels to start with Winnow. F&B to follow up.
EXTERNAL COMMUNICATIOS
| • SG to liaise with Freya and add her to the ESG team /Freya has been added to the group and will join meetings moving forward | Freya to sent a standard format with 3 things to keep simple/concise/to the point - to share with ESG team / Freya looking at PR consultant once we receive guidelines from corporate on industry best practices | Brad to lead on Comms with new format - Email/ Newsletter / P&C for BOH screen display ( 01/09/2022) - Ready this week 5th Sep (first Monday of the month), add to department meeting - ESG awareness comms with/from Freya, Saakshee to follow up | COMPLETED
EMPLOYEE ENGAGEMENT
| • Enhance Green team and make sure continues consistently • Include on Yammer, new TV screens & regular communications to All Teams | Bi-weekly invite already in place. Target - Monthly DEPT meetings /ESG mgs on BOH screens / MSG to include Project + Profitability + SAVINGS MR to assist. | Share the new bottles on Yammer (now called Viva Engage) ALL esg members to complete food waste training so as to lead by example, to be completed by october | COMPLETED
ESG HUB / WASTE MANAGEMENT CHECKLIST
|  | • First two questions: NOT COMPLETED// • Question 3: COMPLETED Questions 4 & 5: NOT COMPLETEDIM to check with Corporate in regards to resources for a self-organised auditTerry to do a small presentation how to read/use data from HEP | No submission on Water MGT Checklist required to Corporate , internal process to be provisioned - Currently ENG have in place - Jonathan has access to pull reports on ESG HUB - key control and measures. Need template and Saakshee will reach out to Caitrine. Share in meetings, record keeping. Create a tab which vendors have, add additional field in Birchstreet. Saakshee will reach out.
|  | • Q1 – NOT COMPLETED • Q2 & 3 – COMPLETED • Q4 & 5 – N/A Ian showed dashboard of ACM waste tracker/ building data | ACM to provide Automated report of Waste / PDM to provide OIL & FOOD report via their portals
AOB
How conscious are we with reducing/ recycling / ESG programme ? |  | Data showed via ACM
What is Hotel's CARBON foot print ?
Reaching out to VENDORs for initiatives/ current practices | Taffryn to start completing vendors initiatives, the rest to follow | Tab created to start to load Green vendors
Mini Bar- BLACK label / Bacardi are Plastic miniature bottles | Are we exploring to Glass/ alternative solution | Beverages 80% - Black label - Doug checking with TRI /HAM. What kind of plastic? Recycle plastic. Pending. | Working on it- to check globally for non plastic use for mini bar items F&B
Touch Point of Hotel / What have wee achieved ? | Filippo and Freya to also complete an internal audit on plastic use in our rooms audit ( non -ops to support) | Departments to check what kind of plastic is used, how many reports, how much paper is used, etc. Flilippo will audit. | Next week Filippo is gathering some information and Engineeering to explore different door knobs. •
Challenges around - Ordering, streamline deliveries to reduce emittions |  | Ian is monitoring. Issue is the approval process, timeline of approval. HOD to do a once a month audit. Create a list and order once. | Alliance spoken to have 3 days delivery in order to reduce footprint/more to come form other vendors
Water bottles for new starters | A welcome box for new starters including a FS metal bottle and notepad | Christian is working on this. Pending. | P&C will focus on this now. IM waiting for samples
Entegra presentation/ discussion | 3 projects to work on: Bees project/ Spout pencil and Hydroponcisis |  | Ian will get some more information - Project bees too expensive. IM in direct talks to sprout pencil, awaiting further info, hydroponcisis was not mentioned!
Community out reach: Maryanne to share with the hotel the Felix project /voluntering project to help others - ongoing
Engineering calling cards | to replace plastic with non plastic calling cards | JT to reach out to his contact and provide feedback
controlling food quantity in ZEST | reduce food waste | Mary-anne to try to find figures on head counts for staff canteen

## 14092022
ESG and Green Team meeting
In Attendance: | Sebastian, Ian, Alex, Filippo, Saakshee, Brad, Ivan, Terry, Maryanne and Fransesco
Absent: | Freya, Baptiste, Agnieszka, Jonathan, Derek, Matthias. |  |  | Last updated 14/09
TOPIC | PLAN OF ACTION/ COMMENTS | UPDATES | ADDITIONAL INFO | STATUS
SINGLE USE OF PLASTICS
Bath amenities | Floris products offered in large format (300ml) in all of our suites & LS guest rooms & the rest of the rollout will be completed by year end 2022 | 95 Rooms to be turned around / KILKER to assign with project led by ENG (Shelving /bathroom) - 2months lead. Kilker working in the price with 3rd part vendor for the stone. | Ivan will update in the next meeting after checking with Vaida. Suggestions made on new shelf to have a hole on the side to avoid mould.
Dry amenities | They have been ordered and waiting for delivery |  | Only combs and shower caps left to use up
Water bottles | • No bottling plant in place as was put on hold before due to cost. • Employees will get aluminium bottles with FS logo. Looked at Chilly bottles brand for now and aim to order 500 bottles • Sporty bottles at coffee/ water station: tried different options but they still have plastic parts and are £1 more expensive per bottle | 4 X Boxes delivered at FSPL - awaiting for rollout (IM) | Care with employees using the bottles for personal use. MR to send communication. Bottles are set up for the running station and by the coffee station in the lobby.
My Bar | • Currently offering Evian plastic bottle / Search different options Look at Acqua Panna product as an option – IM/ FG | A/Panna to stay in minibar /comp offering as part of switch over | DONE, price change pending with FDS / Opera | COMPLETED
Laundry presentation | • Fabric cover presented at the moment for guests. Basket with paper cover and hanger has no cover • For employees – when done in-house there is no cover but when done outside the company send with a plastic cover • Plastic roll in HSKP to be replaced with more eco friendly option. IC to liaise with Silvia Grey to check if they have other non-plastic options. IM to confirm completion date | Sylvia Grey Agreed with Plastic free and Valet using recyclable plastic | Scott Taber - 19/09/22- PLASTIC FREE FSPL already switched internally, pending SG, change to biodegradable
F&B disposables | • All plastic free already, however FG to check if take away lids are biodegradable and PLA free too | Few PLA Lids remains that is non recyclable (stock to be finished in few weeks) / New order are Recyclable Lids at FSPL 17/08/2022 | Ian placed order - TBC Bins: Leave glass bins, cannot buy bins with lid due to hygiene reasons. - Plastic bag in the pantries (training required for staff) | complete
Straws | • All plastic free already |  |  | COMPLETE
Recycling | • Suggestions of including recycling bins in guest rooms may be pointless as there is no segregation and they may go to the same place • HSKP Pantries segregation bins to be removed. | HSK req for redesign Pantry for 3 BINS - Bins are to be emptied more frequently but posses a challenge ( IM to review current provision/ order / ENG to support with shelving)
Soap recycling | • Working with La Bottega that can recycle | IC to start process with La Bottega. To use old soap from old recycling projects. | Start with one floor
SUSTAINABLE F&B
Food waste training | • For all F&B employees – 30 minutes video with quiz at the end. MR to check with Cristina if we can send to all F&B employees to complete and look into embedding into EMBARK in the future. Deadline was end of Q2/2022 | CH (P&C) - agreed to put in training in Work Day and commencing 1st SEP 2022 / Two types of training ( F&B - EMABARK & 2. 30 Min Work Day training) | Cristina will send out a list on 1st of Sep. Email sent
Food waste diversion | • Issues with local legislation, so park for now ( Park for now due to local laws restrictions) | By law FSPL can donate - FOOD to charity - awaiting nominated Partnership list from Corporate . | Saakshee will send out an email to Caitrin VP ESG. Email sent
Food donation programs | To explore - staff dropping off initiative TO/FROM to work for homeless (awaiting more info on Product waste / quantity/packing provisions) | Logistic might be a problem for consistency on PICK up /DROP off on food donation
Food waste AI solutions | • Nothing in place here • There was a pilot programme happening at FS New Orleans and Dubai but no news yet on how has developed, successes and ROI examples to check with Corporate office if there have been some results from that pilot as yet | Waiting for Gianluca for the results/ we have budget alocated for Q3 | Winnow - Francesco to follow up with corporate for further details, all hotels to start with Winnow.
EXTERNAL COMMUNICATIOS
| • SG to liaise with Freya and add her to the ESG team /Freya has been added to the group and will join meetings moving forward | Freya to sent a standard format with 3 things to keep simple/concise/to the point - to share with ESG team / Freya looking at PR consultant once we receive guidelines from corporate on industry best practices | Brad to lead on Comms with new format - Email/ Newsletter / P&C for BOH screen display ( 01/09/2022) - Ready this week 5th Sep (first Monday of the month), add to department meeting | COMPLETED
EMPLOYEE ENGAGEMENT
| • Enhance Green team and make sure continues consistently • Include on Yammer, new TV screens & regular communications to All Teams | Bi-weekly invite already in place. Target - Monthly DEPT meetings /ESG mgs on BOH screens / MSG to include Project + Profitability + SAVINGS MR to assist. | Share the new bottles on Yammer (now called Viva Engage) | COMPLETED
ESG HUB / WASTE MANAGEMENT CHECKLIST
|  | • First two questions: NOT COMPLETED// • Question 3: COMPLETED Questions 4 & 5: NOT COMPLETEDIM to check with Corporate in regards to resources for a self-organised auditTerry to do a small presentation how to read/use data from HEP | No submission on Water MGT Checklist required to Corporate , internal process to be provisioned - Currently ENG have in place - Jonathan has access to pull reports on ESG HUB - key control and measures. Need template and Saakshee will reach out to Caitrine. Share in meetings, record keeping. Create a tab which vendors have, add additional field in Birchstreet. Saakshee will reach out.
|  | • Q1 – NOT COMPLETED • Q2 & 3 – COMPLETED • Q4 & 5 – N/A Ian showed dashboard of ACM waste tracker/ building data | ACM to provide Automated report of Waste / PDM to provide OIL & FOOD report via their portals
AOB
How conscious are we with reducing/ recycling / ESG programme ? |  | Data showed via ACM
What is Hotel's CARBON foot print ?
Reaching out to VENDORs for initiatives/ current practices | Taffryn to start completing vendors initiatives, the rest to follow | Tab created to start to load Green vendors
Mini Bar- BLACK label / Bacardi are Plastic miniature bottles | Are we exploring to Glass/ alternative solution | Beverages 80% - Black label - Doug checking with TRI /HAM. What kind of plastic? Recycle plastic. Pending. | Working on it
Touch Point of Hotel / What have wee achieved ? | Filippo and Freya to also complete an internal audit on plastic use in our rooms audit ( non -ops to support) | Departments to check what kind of plastic is used, how many reports, how much paper is used, etc. Flilippo will audit. | Next week Filippo is gathering some information and Engineeering to explore different door knobs. •
Challenges around - Ordering, streamline deliveries to reduce emittions |  | Ian is monitoring. Issue is the approval process, timeline of approval. HOD to do a once a month audit. Create a list and order once. | Alliance spoken to have 3 days delivery in order to reduce footprint/more to come form other vendors
Water bottles for new starters | A welcome box for new starters including a FS metal bottle and notepad | Christian is working on this. Pending. | P&C will focus on this now.
Entegra presentation/ discussion | 3 projects to work on: Bees project/ Spout pencil and Hydroponcisis |  | Ian will get some more information
Community out reach: Maryanne to share with the hotel the Felix project /voluntering project to help others

## 31082022
ESG and Green Team meeting
In Attendance: | Doug, Michiko, Sebastian, Ian, Alex, Filippo, Ramesh, Saakshee, Brad, Taffryn, Ivan, Terry
Absent: | Freya, Baptiste, Agnieszka, Jonathan, Derek, Matthias, Matthew, |  |  | Last updated 31.08.2022
TOPIC | PLAN OF ACTION/ COMMENTS | UPDATES | ADDITIONAL INFO | STATUS
SINGLE USE OF PLASTICS
Bath amenities | Floris products offered in large format (300ml) in all of our suites & LS guest rooms & the rest of the rollout will be completed by year end 2022 | 95 Rooms to be turned around / KILKER to assign with project led by ENG (Shelving /bathroom) - 2months lead | Ivan will update in the next meeting after checking with Vaida. Suggestions made on new shelf to have a hole on the side to avoid mould.
Dry amenities | They have been ordered and waiting for delivery |  | Only combs and shower caps left to use up
Water bottles | • No bottling plant in place as was put on hold before due to cost. • Employees will get aluminium bottles with FS logo. Looked at Chilly bottles brand for now and aim to order 500 bottles • Sporty bottles at coffee/ water station: tried different options but they still have plastic parts and are £1 more expensive per bottle | 4 X Boxes delivered at FSPL - awaiting for rollout (IM) | Care with employees using the bottles for personal use. MR to send communication. Bottles are set up for the running station and by the coffee station in the lobby.
My Bar | • Currently offering Evian plastic bottle / Search different options Look at Acqua Panna product as an option – IM/ FG | A/Panna to stay in minibar /comp offering as part of switch over | DONE, price change pending with FDS / Opera | COMPLETED
Laundry presentation | • Fabric cover presented at the moment for guests. Basket with paper cover and hanger has no cover • For employees – when done in-house there is no cover but when done outside the company send with a plastic cover • Plastic roll in HSKP to be replaced with more eco friendly option. IC to liaise with Silvia Grey to check if they have other non-plastic options. IM to confirm completion date | Sylvia Grey Agreed with Plastic free and Valet using recyclable plastic | Scott Taber - 19/09/22- PLASTIC FREE FSPL already switched internally, pending SG, change to biodegradable
F&B disposables | • All plastic free already, however FG to check if take away lids are biodegradable and PLA free too | Few PLA Lids remains that is non recyclable (stock to be finished in few weeks) / New order are Recyclable Lids at FSPL 17/08/2022 | Ian placed order - TBC Bins: Leave glass bins, cannot buy bins with lid due to hygiene reasons. - Plastic bag in the pantries (training required for staff)
Straws | • All plastic free already |  |  | COMPLETE
Recycling | • Suggestions of including recycling bins in guest rooms may be pointless as there is no segregation and they may go to the same place • HSKP Pantries segregation bins to be removed. | HSK req for redesign Pantry for 3 BINS - Bins are to be emptied more frequently but posses a challenge ( IM to review current provision/ order / ENG to support with shelving)
Soap recycling | • Working with La Bottega that can recycle | IC to start process with La Bottega | Start with one floor
SUSTAINABLE F&B
Food waste training | • For all F&B employees – 30 minutes video with quiz at the end. MR to check with Cristina if we can send to all F&B employees to complete and look into embedding into EMBARK in the future. Deadline was end of Q2/2022 | CH (P&C) - agreed to put in training in Work Day and commencing 1st SEP 2022 / Two types of training ( F&B - EMABARK & 2. 30 Min Work Day training) | Cristina will send out a list on 1st of Sep.
Food waste diversion | • Issues with local legislation, so park for now ( Park for now due to local laws restrictions) | By law FSPL can donate - FOOD to charity - awaiting nominated Partnership list from Corporate . | Saakshee will send out an email to Caitrin VP ESG
Food donation programs | To explore - staff dropping off initiative TO/FROM to work for homeless (awaiting more info on Product waste / quantity/packing provisions) | Logistic might be a problem for consistency on PICK up /DROP off on food donation
Food waste AI solutions | • Nothing in place here • There was a pilot programme happening at FS New Orleans and Dubai but no news yet on how has developed, successes and ROI examples to check with Corporate office if there have been some results from that pilot as yet |  | Winnow - Francesco to follow up with corporate for further details, all hotels to start with Winnow
EXTERNAL COMMUNICATIOS
| • SG to liaise with Freya and add her to the ESG team /Freya has been added to the group and will join meetings moving forward | Freya to sent a standard format with 3 things to keep simple/concise/to the point - to share with ESG team / Freya looking at PR consultant once we receive guidelines from corporate on industry best practices | Brad to lead on Comms with new format - Email/ Newsletter / P&C for BOH screen display ( 01/09/2022) - Ready this week 5th Sep (first Monday of the month), add to department meeting | COMPLETED
EMPLOYEE ENGAGEMENT
| • Enhance Green team and make sure continues consistently • Include on Yammer, new TV screens & regular communications to All Teams | Bi-weekly invite already in place. Target - Monthly DEPT meetings /ESG mgs on BOH screens / MSG to include Project + Profitability + SAVINGS MR to assist. | Share the new bottles on Yammer (now called Viva Engage) | COMPLETED
ESG HUB / WASTE MANAGEMENT CHECKLIST
|  | • First two questions: NOT COMPLETED • Question 3: COMPLETED Questions 4 & 5: NOT COMPLETEDIM to check with Corporate in regards to resources for a self-organised audit | No submission on Water MGT Checklist required to Corporate , internal process to be provisioned - Currently ENG have in place - Jonathan has access to pull reports on ESG HUB - key control and measures. Need template and Saakshee will reach out to Caitrine. Share in meetings, record keeping. Create a tab which vendors have, add additional field in Birchstreet. Saakshee will reach out.
|  | • Q1 – NOT COMPLETED • Q2 & 3 – COMPLETED • Q4 & 5 – N/A | ACM to provide Automated report of Waste / PDM to provide OIL & FOOD report via their portals
AOB
How conscious are we with reducing/ recycling / ESG programme ?
What is Hotel's CARBON foot print ?
Reaching out to VENDORs for initiatives/ current practices |  | Tab created to start to load Green vendors
Mini Bar- BLACK label / Bacardi are Plastic miniature bottles | Are we exploring to Glass/ alternative solution | Beverages 80% - Black label - Doug checking with TRI /HAM. What kind of plastic? Recycle plastic. Pending.
Touch Point of Hotel / What have wee achieved ? | Filippo and Freya to also complete an internal audit on plastic use in our rooms audit ( non -ops to support) | Departments to check what kind of plastic is used, how many reports, how much paper is used, etc. Flilippo will audit.
Challenges around - Ordering, streamline deliveries to reduce emittions |  | Ian is monitoring. Issue is the approval process, timeline of approval. HOD to do a once a month audit. Create a list and order once.
Water bottles for new starters | A welcome box for new starters including a FS metal bottle and notepad | Christian is working on this. Pending.

## 17082022
ESG and Green Team meeting
Last updated 18.08.2022
TOPIC | PLAN OF ACTION/ COMMENTS | UPDATES | ADDITIONAL INFO | STATUS
SINGLE USE OF PLASTICS
Bath amenities | Floris products offered in large format (300ml) in all of our suites & LS guest rooms & the rest of the rollout will be completed by year end 2022 | 95 Rooms to be turned around / KILKER to assign with project led by ENG (Shelving /bathroom) - 2months lead | Ivan will update in the next meeting after checking with Vaida. Suggestions made on new shelf to have a hole on the side to avoid mould.
Dry amenities | They have been ordered and waiting for delivery |  | Still waiting.
Water bottles | • No bottling plant in place as was put on hold before due to cost. • Employees will get aluminium bottles with FS logo. Looked at Chilly bottles brand for now and aim to order 500 bottles • Sporty bottles at coffee/ water station: tried different options but they still have plastic parts and are £1 more expensive per bottle | 4 X Boxes delivered at FSPL - awaiting for rollout (IM) | Care with employees using the bottles for personal use. MR to send communication. Bottles are set up for the running station and by the coffee station in the lobby.
My Bar | • Currently offering Evian plastic bottle / Search different options Look at Acqua Panna product as an option – IM/ FG | A/Panna to stay in minibar /comp offering as part of switch over | DONE, price change pending with FDS / Opera
Laundry presentation | • Fabric cover presented at the moment for guests. Basket with paper cover and hanger has no cover • For employees – when done in-house there is no cover but when done outside the company send with a plastic cover • Plastic roll in HSKP to be replaced with more eco friendly option. IC to liaise with Silvia Grey to check if they have other non-plastic options. IM to confirm completion date | Sylvia Grey Agreed with Plastic free and Valet using recyclable plastic | Scott Taber - 19/09/22- PLASTIC FREE FSPL already switched internally, pending SG, change to biodegradable
F&B disposables | • All plastic free already, however FG to check if take away lids are biodegradable and PLA free too | Few PLA Lids remains that is non recyclable (stock to be finished in few weeks) / New order are Recyclable Lids at FSPL 17/08/2022 | Ian placed order - TBC Bins: Leave glass bins, cannot buy bins with lid due to hygiene reasons.
Straws | • All plastic free already |  |  | COMPLETE
Recycling | • Suggestions of including recycling bins in guest rooms may be pointless as there is no segregation and they may go to the same place • HSKP Pantries segregation bins to be removed. | HSK req for redesign Pantry for 3 BINS - Bins are to be emptied more frequently but posses a challenge ( IM to review current provision/ order / ENG to support with shelving) | - Plastic bag in the pantries (training required for staff)
Soap recycling | • Working with La Bottega that can recycle | IC to start process with La Bottega | Start with one floor
SUSTAINABLE F&B
Food waste training | • For all F&B employees – 30 minutes video with quiz at the end. MR to check with Cristina if we can send to all F&B employees to complete and look into embedding into EMBARK in the future. Deadline was end of Q2/2022 | CH (P&C) - agreed to put in training in Work Day and commencing 1st SEP 2022 / Two types of training ( F&B - EMABARK & 2. 30 Min Work Day training) | Cristina will send out a list on 1st of Sep.
Food waste diversion | • Issues with local legislation, so park for now ( Park for now due to local laws restrictions) | By law FSPL can donate - FOOD to charity - awaiting nominated Partnership list from Corporate . | Saakshee will send out an email to Caitrin VP ESG
Food donation programs | To explore - staff dropping off initiative TO/FROM to work for homeless (awaiting more info on Product waste / quantity/packing provisions) | Logistic might be a problem for consistency on PICK up /DROP off on food donation
Food waste AI solutions | • Nothing in place here • There was a pilot programme happening at FS New Orleans and Dubai but no news yet on how has developed, successes and ROI examples to check with Corporate office if there have been some results from that pilot as yet |  | Winnow - Francesco to follow up with corporate for further details, all hotels to start with Winnow
EXTERNAL COMMUNICATIOS
| • SG to liaise with Freya and add her to the ESG team /Freya has been added to the group and will join meetings moving forward | Freya to sent a standard format with 3 things to keep simple/concise/to the point - to share with ESG team / Freya looking at PR consultant once we receive guidelines from corporate on industry best practices | Brad to lead on Comms with new format - Email/ Newsletter / P&C for BOH screen display ( 01/09/2022) - Ready this week 5th Sep (first Monday of the month), add to department meeting
EMPLOYEE ENGAGEMENT
| • Enhance Green team and make sure continues consistently • Include on Yammer, new TV screens & regular communications to All Teams | Bi-weekly invite already in place. Target - Monthly DEPT meetings /ESG mgs on BOH screens / MSG to include Project + Profitability + SAVINGS MR to assist. | Share the new bottles on Yammer (now called Viva Engage)
ESG HUB / WASTE MANAGEMENT CHECKLIST
|  | • First two questions: NOT COMPLETED • Question 3: COMPLETED Questions 4 & 5: NOT COMPLETEDIM to check with Corporate in regards to resources for a self-organised audit | No submission on Water MGT Checklist required to Corporate , internal process to be provisioned - Currently ENG have in place - Jonathan has access to pull reports on ESG HUB - key control and measures. Need template and Saakshee will reach out to Caitrine. Share in meetings, record keeping. Create a tab which vendors have, add additional field in Birchstreet. Saakshee will reach out.
|  | • Q1 – NOT COMPLETED • Q2 & 3 – COMPLETED • Q4 & 5 – N/A | ACM to provide Automated report of Waste / PDM to provide OIL & FOOD report via their portals
AOB
How conscious are we with reducing/ recycling / ESG programme ?
What is Hotel's CARBON foot print ?
Reaching out to VENDORs for initiatives/ current practices
Mini Bar- BLACK label / Bacardi are Plastic miniature bottles | Are we exploring to Glass/ alternative solution | Beverages 80% - Black label - Doug checking with TRI /HAM. What kind of plastic? Recycle plastic. Pending.
Touch Point of Hotel / What have wee achieved ? | Filippo and Freya to also complete an internal audit on plastic use in our rooms audit ( non -ops to support) | Departments to check what kind of plastic is used, how many reports, how much paper is used, etc. Flilippo will audit.
Challenges around - Ordering, streamline deliveries to reduce emittions |  | Ian is monitoring. Issue is the approval process, timeline of approval. HOD to do a once a month audit. Create a list and order once.
Water bottles for new starters | A welcome box for new starters including a FS metal bottle and notepad | Christian is working on this. Pending.

## ESG Corporate Q's
ESG Corporate Q's to ask
Name | Department | Q | Y/N
Freya Costello | PR | Is there a corporate directive/guidance on what level of info/frequency of ESG initiatoves can be shared on social. | Corp Teams coming up with a name/vision for ESG to go to market with. Small stories can be shared
Jade Chang | Sales | Are we still looking into a general landing page that can cover ESG questions for sales clients? in the works trust.fourseasons.com, esg, safety and security, protected, only those that need access will have it | It is in the works, looking into devleoping a site with ESG data (protected) with select access. Incase of specific Q's - redirect to Corporate ESG Teams.
Maryanne Raasch | P&C | Do we have slides to be included in EMBARK or do we have the freedom to create our local ones? | Slides from ESG team have been sent to corporate L&D teams, generic slides are there & Caitrin will share them with FSPL. Talks about DIB in general.
Derek Rostel |  | Any insight/guidance on CSR initiatives. | A CSR playbook and focus on the Social pillar on ESG portal will be shared and the new playbook will be issued soon. In final stages of review & will be sent to FSPL for initial comments.
Saakshee Gahlawat | Exec Office | The direction on FOH keys - any alternative to plastic (except wood) & given mobile key isnt compatible with Android phones. | Ok to keep using plastic keys as long as they are recycled. Cardboard keys are an option, however will not be an option for FSPL due to encryption
|  | HEP Portal survey completion frequency? | 6th Feb being launched and to be completed by 31st March. Being revised, few extra Q's focusing on Social element. Survey is to be completed once a year.
|  | Any specific concerns/areas of oppurtuities from corporate teams about FSPL ESG initiatves based on last HEP Survey update? | Overall quite balanced - keep working on newer opportuities.
Francesco Galletti | F&B | What %age of minibar needs to be plastic free? Is it 100% - if so, some top performing items will need to be dropped which may not be as financially appropriate. | Popcorn to be replaced, smaller items (coco water.chocolate bars - Kit kat/snacks) is ok.
|  | Currently all explored options of food donation programmes are at a cost which isnt budgeted, if the wastage is reduced (which is being monitored) is a food donation partner a must have? | An exception will be made for FSPL for 2023, due to ongoing restaurant renovation/reduced banqueting ops & no vendors found on pick up charges, most have monthly subscription.
|  | Winnow is currently not budgeted for 2023 for FSPL due to overall Winnow model being more conducive to large scale F&B ops. This will continue to be a non compliance for us for atleast 2023. | Winnow for 2023 can be exempt for FSPL, possibly use for Zest & explore that option.
|  | Any stipulation expected on Food Waste training completion for non F&B departments? | F&B is at 100%. Non F&B departments at 47% completion. Shall continue to strive for 80% non F&B departments.
|  | Is there any requirement to be 100% plastic free even from a kitchen equipment perspective (pauches, cling film)? | No suitable alternatives at the moment, corporate teams looking at options. Ok to keep using as is.
Amanda Grant | Catering | Do the dietary benchmarks apply to Banqueting Menus as well? Ie Two Starters, Two Mains and One Dessert. sharing' if we feel appropriate to do so with client/ company? | Not stipulated for Catering, but good starting point and recommended as & when possible.
Ian Maynard | Purchasing | Should we be looking at Staff catering as well at this time or will this be a later roll out? If we are to do it now is there an accepable level for example yougarts in plastic tubs is this accepable? | Work on some options for smaller tweaks (replacing ketchup/mayo to larger bottles). At this point no conflict with LWC practices for large format amenities.

## Vendors
GREEN VENDORS |  |  |  | GREEN
Name | Contact | Department | Summary of Green Services | Y/N